## Sheet1
Date | Day | Work | Hours Approx
2019-04-12 | Friday | Planning | 2
2019-04-15 | Monday | Requirement Listing | 3
2019-04-16 | Tuesday | Name Electronics, Components Order(FPS) | 2
2019-04-17 | Wednesday | Components Order(OLED,Ethernet,Mega,RTC) | 2
2019-04-19 | Friday | Arduino Testing | 4
2019-04-22 | Monday | Components Checking | 3
2019-04-24 | Wednesday | OLED Exchange Mail, Name Electronics(BreadBoard) | -
2019-04-28 | Sunday | New Character LCD | 2
2019-04-29 | Monday | Button Cell for RTC,LED Blink | 4
2019-05-02 | Thursday | FPS Testing, Name Electronics(Jumper Wires) | 4
2019-05-03 | Friday | Project Design - Mind Map | 2
2019-05-09 | Thursday | Prototype Servlet Start, | 11
2019-05-11 | Saturday | Membrane Keypad | 13
2019-05-13 | Monday | ER Diagram | 2
2019-05-15 | Wednesday | MDF Container, Admin, Subject Management | 19
2019-05-17 | Friday | Finger Identifaction | 11
2019-05-22 | Wednesday | Finger Enrollment | 17
2019-05-25 | Saturday | Database Design | 6
2019-06-02 | Sunday | Database Connection | 2
2019-06-04 | Tuesday | Ethernet Connection | 21
2019-06-07 | Friday | Excel Upload Servlet | 8
2019-06-08 | Saturday | Student Detail Servlet | 10
2019-06-11 | Tuesday | Timetable Servlet | 11
2019-06-13 | Thursday | Bugs and Errors (Servlet) | 15
2019-06-15 | Saturday | Complete Integration | 20
2019-06-17 | Monday | Bugs and Errors | 7
2019-06-19 | Wednesday | Planning | 4
2019-06-20 | Thursday | Information Gathering | 3
2019-06-22 | Saturday | Teacher Intimation | -
2019-07-01 | Monday | Planning and Design | 3
2019-07-03 | Wednesday | HOD Sir Permission | -
2019-07-15 | Monday | Mitali Maam | -
2019-07-16 | Tuesday | Presentation Intro | -
2019-07-17 | Wednesday | Polytechnic Reference | -
2019-07-19 | Friday | Architechture and Bugs | 3
2019-07-22 | Monday | Polytechnic for SPI Bug
2019-07-24 | Wednesday | Bugs and Errors | 3
2019-07-29 | Monday | Bugs and Errors | 3
2019-08-02 | Friday | Database Design Reloaded | 5
2019-08-03 | Saturday | GUI Reloaded | 4
2019-08-05 | Monday | Startup Form | -
2019-08-07 | Wednesday | Logo | 3
2019-08-08 | Thursday | Polytechnic for Startup Fund | -
2019-08-09 | Friday | MicroProcessor Research | 4
2019-08-10 | Saturday | Login Rebirth | 5
2019-08-11 | Sunday | GUI Update | 3
2019-08-12 | Monday | Raspeberry Pi Begins | 5
2019-08-16 | Friday | OTP with Email | 5
2019-08-17 | Saturday | Real MySQL Escape | 2
2019-08-20 | Tuesday | Fingerprint Template Generation | 15
2019-08-22 | Thursday | Startup Detail Gathering (Pavillion) | -
|  | Internal Exams | -
2019-09-01 | Sunday | Switch to Github | 6
2019-09-03 | Tuesday | Fingerprint Research, RTC with Rpi | 4
2019-09-04 | Wednesday | Screen with Rpi, Figuring Git | 5
2019-09-05 | Thursday | Unlimited Fingerprint Milestone | 18
2019-09-06 | Friday | Fingerprint Testing | 8
2019-09-08 | Sunday | Netbeans with Git | 3
2019-09-09 | Monday | Organization on Github | 4
2019-09-10 | Tuesday | Database Rebirth | 15
2019-09-12 | Thursday | Rpi Sync Function | 13
2019-09-13 | Friday | SQL just got crazy | 5
|  | Practical Exams | -
2019-09-24 | Tuesday | Bugs GUI | 2
2019-09-26 | Thursday | Documentation | 4
358