## Sheet1
Date | Working Hours |  |  | Total Hours | Worked on which Task |  |  | Total Task Completed
| Ebenezer | Husein | Vraj |  | Ebenezer | Husein | Vraj
Thursday, September 26, 2019 |  | 5 |  | 5 |  | Fixed navbar, fixed google recaptcha, fixed modal box and added splash screen |  | 4
2019-09-27 | 9 |  | 8 | 17 | Rpi demo debugging, light show, perf board designing |  | Documentation, Order from ROBU | 4
2019-09-28 | 5 |  | 0 | 5 | perf board adding modules - eth, rtc |  | - | 1
2019-09-29 | 9 |  | 0 | 9 | buzzer function, perf board adding modules - rtc, fps, buzzer |  | - | 3
2019-09-30 | 0 |  | 3 | 3 |  |  | sql queries, manage timetable | 2
2019-10-01 | 8 |  | 0.5 | 8.5 | lcd testing |  | Rpi testing with projecting gui | 1
2019-10-02 | 7 | 5 | 7 | 19 | lcd testing | Sidebar button and Query for Subject table | editTimetable Servlet, Database(MAJOR), ERD | 5
2019-10-03 | 5 | 3 | 2 | 10 | lcd testing | Added dispSubject, editSubject and addSubject Servlets | minor changes in servlet | 4
2019-10-04 | 4 | 1 | 4 | 9 | servlets,finance | Added deltSubject Servlet | servlets, validations, finance | 6
2019-10-05 | 7 |  | 1 | 8 | enroll funciton |  | Documentation | 1
2019-10-06 | 3 |  | 0 | 3 | rpi reinstallation |  | - | 0
2019-10-07 | 13 |  | 8 | 21 | adv enroll, save timetable, session management, distimetable |  | Database, Servlets(Session), GUI | 3
2019-10-08 |  | 4 | 1 | 5 |  | Accordion Side menu |  | 1
2019-10-09 |  | 3 |  | 3 |  | Added CSS in editSubject Servlet |  | 1
2019-10-10
2019-10-11
2019-10-12
2019-10-13
2019-10-14
2019-10-15
2019-10-16
2019-10-17
2019-10-18
2019-10-19
2019-10-20
2019-10-21
2019-10-22
2019-10-23
2019-10-24
2019-10-25
2019-10-26
2019-10-27
2019-10-28
2019-10-29
2019-10-30
2019-10-31
Grand Total hours | 70 | 21 | 34.5 | 120.5 |  |  | Total Tasks completed | 32