## Sheet1
Date | Working Hours |  |  | Total Man Hours | Worked on which Task |  |  | Total Task Completed
| Ebenezer | Husein | Vraj |  | Ebenezer | Husein | Vraj
Thursday, September 26, 2019 | 0 | 5 | 0 | 5 |  | Fixed navbar, fixed google recaptcha, fixed modal box and added splash screen |  | 4
2019-09-27 | 9 | 0 | 8 | 17 | Rpi demo debugging, light show, perf board designing | - | Documentation, Order from ROBU | 4
2019-09-28 | 5 | 0 | 0 | 5 | perf board adding modules - eth, rtc | - | - | 1
2019-09-29 | 9 | 0 | 0 | 9 | buzzer function, perf board adding modules - rtc, fps, buzzer | - | - | 3
2019-09-30 | 0 | 0 | 3 | 3 | - | - | sql queries, manage timetable | 2
| - | - | -
2019-10-01 | 8 | 0 | 0.5 | 8.5 | lcd testing |  | Rpi testing with projecting gui | 1
2019-10-02 | 7 | 5 | 7 | 19 | lcd testing | Sidebar button and Query for Subject table | editTimetable Servlet, Database(MAJOR), ERD | 5
2019-10-03 | 5 | 3 | 2 | 10 | lcd testing | Added dispSubject, editSubject and addSubject Servlets | minor changes in servlet | 4
2019-10-04 | 4 | 1 | 4 | 9 | servlets,finance | Added deltSubject Servlet | servlets, validations, finance | 5
2019-10-05 | 7 | 0 | 1 | 8 | enroll funciton | - | Documentation | 1
2019-10-06 | 3 | 0 | 0 | 3 | rpi reinstallation | - | - | 0
2019-10-07 | 13 | 0 | 8 | 21 | adv enroll , session management, distimetable | - | Database, Servlets(Session), GUI | 5
2019-10-08 | 8 | 4 | 1 | 13 | display timetable and new gui | Accordion Side menu | GUI changes | 4
2019-10-09 | 7 | 3 | 2 | 12 | display student details | Added CSS in editSubject Servlet | editStudent servlet | 4
2019-10-10 | 8 | 0 | 3 | 11 | adv new week function | - | editStudent, AJAX, validations | 4
2019-10-11 | 9 | 0 | 1 | 10 | add/delete faculty | - | Bugs, Testing, Documentation | 4
2019-10-12 | 7 | 0 | 0 | 7 | add student | - | - | 2
2019-10-13 | 4 | 0 | 0 | 4 | minor bug fixes | - | - | 1
2019-10-14 | 0 | 0 | 0 | 0 | - | - | - | 1
2019-10-15 | 0 | 0 | 0 | 0 | - | - | - | -
2019-10-16 | 0 | 0 | 0 | 0 | - | - | - | -
2019-10-17 | 0 | 1.5 | 0 | 1.5 | - | Fixed image in navbar, added css in editStudent, editFaculty, editTimetable Servlets | - | 2
2019-10-18 | 0 | 0 | 0 | 0 | - | - | - | -
2019-10-19 | 0 | 0 | 0 | 0 | - | - | -
2019-10-20 | 2 | 0 | 1 | 3 | listing pending work, identifing major bugs | - | ajaxCheckRoll | 3
2019-10-21 | 12 | 8.5 | 3 | 23.5 | performance tweeks, view subject , subject attendance | editProfile page and editProfile servlet | addStudent | 6
2019-10-22 | 10 | 4 | 5 | 19 | minimizer and profile pic upload | editProfile servlet | addStudent, photoblob in database, deleteStudent | 3
2019-10-23 | 9 | 5 | 6 | 20 | GUI, profile pic for students | Fixed navbar in faculty login, removed navbar & set content to center in main login page | batches and subject in addStudent, session start, detailing, dependencies, db relations | 9
2019-10-24 | 11 | 6.5 | 6 | 23.5 | preferences for combined timetable, disable on labs completed | shake effect and table | ajax on Index | 3
2019-10-25 | 5 | 0 | 5 | 10 | bug fixes, add student, unselectable text, | - | addStudent bugs, studentProgression | 5
2019-10-26 | 5 | 7 | 0 | 12 | fixed new week redundancy | homepage navbar | D | 2
2019-10-27 | 0 | 5 | 0 | 5 | - | fixed homepage navbar and custom scroll bar and table css | I | 2
2019-10-28 | 5 | 0 | 0 | 5 | time based timetable edit, fix date printing | - | W | 2
2019-10-29 | 12 | 0 | 0 | 12 | convert full site to ajax | - | A | 1 | /DEADLINE earlier
2019-10-30 | 5 | 2 | 0 | 7 | convert full site to ajax | Logo animation | L | 2
2019-10-31 | 0 | 0 | 0 | 0 | convert full site to ajax | - | I
| - | - | -
2019-11-01 | 5 | 0 | 0 | 5 | convert full site to ajax | - | -
2019-11-02 | 13 | 0 | 0 | 13 | convert full site to ajax | - | -
2019-11-03 | 9 | 0 | 1 | 10 | convert full site to ajax | - | Bought acryllic Sheet | 1
2019-11-04 | 6 | 3.5 | 6.5 | 16 | convert full site to ajax | splash screen | merge branch, box design | 2
2019-11-05 | 5 | 0 | 4 | 9 | ajax bug fix | - | finance, logos, progression wizard GUI, POI | 3
2019-11-06 | 9 | 0 | 8 | 17 | subject selection bugs, slot management | - | sheet cutting, box design | 2
2019-11-07 | 9 | 1 | 8 | 18 | new gui, session management | splash screen | box design, Database Queries, Dummy Data | 6
2019-11-08 | 7 | 0 | 5 | 12 | gui bugs, data tables | - | Dummy Data, database Query, reporting, documentation | 5
2019-11-09 | 9 | 0 | 4 | 13 | save stud details | - | testing, database to excel | 2
2019-11-10 | 5 | 0 | 0 | 5 | save stud details , back button | - | -
2019-11-11 | 8 | 4 | 7 | 19 | subject batch for students, back button bug fix | background | Separate photoID database, merge branch, db to excel(POI) | 4
2019-11-12 | 5 | 0 | 3 | 8 | soldering rpi keypad and fit inside box | - | documentation, reporting | 3
2019-11-13 | 0 | 2 | 8 | 10 | - | background | progression updated | 1
2019-11-14 | 0 | 0 | 0 | 0 | - | - | -
2019-11-15 | 0 | 2 | 3 | 5 | - | background and dropdowns CSS | progression, documentation | 2
2019-11-16 |  | 5 |  | 5 |  | fixed resetpassword page and added css to editSlot |  | 2
2019-11-17 |  |  |  | 0
2019-11-18 |  |  |  | 0
2019-11-19 |  |  |  | 0
2019-11-20 |  |  |  | 0
2019-11-21 |  |  |  | 0
2019-11-22 |  |  |  | 0
2019-11-23 |  |  |  | 0
2019-11-24 |  |  |  | 0
2019-11-25 |  |  |  | 0
2019-11-26 |  |  |  | 0
2019-11-27 |  |  |  | 0
2019-11-28 |  |  |  | 0
2019-11-29 |  |  |  | 0
2019-11-30 |  | 0.5 |  | 0.5 |  | About us page
2019-12-01 |  |  |  | 0
2019-12-02 |  | 5 |  | 5 |  | About us Page, hover in login page and editStudDetails javascipt |  | 2
2019-12-03 |  |  |  | 0
Grand Total hours | 279 | 83.5 | 124 | 486.5 |  |  | Total Tasks completed | 130