## Sheet1
Day Count | Date | Day | Work | Hours Approx
Day1 | 2019-04-12 | Friday | Planning | 2
Day2 | 2019-04-15 | Monday | Requirement Listing | 3
Day3 | 2019-04-16 | Tuesday | Name Electronics, Components Order(FPS) | 2
Day4 | 2019-04-17 | Wednesday | Components Order(OLED,Ethernet,Mega,RTC) | 2
Day5 | 2019-04-19 | Friday | Arduino Testing | 4
Day6 | 2019-04-22 | Monday | Components Checking | 3
Day7 | 2019-04-24 | Wednesday | OLED Exchange Mail, Name Electronics(BreadBoard) | -
Day8 | 2019-04-28 | Sunday | New Character LCD | 2
Day9 | 2019-04-29 | Monday | Button Cell for RTC,LED Blink | 4
Day10 | 2019-05-02 | Thursday | FPS Testing, Name Electronics(Jumper Wires) | 4
Day11 | 2019-05-03 | Friday | Project Design - Mind Map | 2
Day12 | 2019-05-09 | Thursday | Prototype Servlet Start, | 11
Day13 | 2019-05-11 | Saturday | Membrane Keypad | 13
Day14 | 2019-05-13 | Monday | ER Diagram | 2
Day15 | 2019-05-15 | Wednesday | MDF Container, Admin, Subject Management | 19
Day16 | 2019-05-17 | Friday | Finger Identifaction | 11
Day17 | 2019-05-22 | Wednesday | Finger Enrollment | 17
Day18 | 2019-05-25 | Saturday | Database Design | 6
Day19 | 2019-06-02 | Sunday | Database Connection | 2
Day20 | 2019-06-04 | Tuesday | Ethernet Connection | 21
Day21 | 2019-06-07 | Friday | Excel Upload Servlet | 8
Day22 | 2019-06-08 | Saturday | Student Detail Servlet | 10
Day23 | 2019-06-11 | Tuesday | Timetable Servlet | 11
Day24 | 2019-06-13 | Thursday | Bugs and Errors (Servlet) | 15
Day25 | 2019-06-15 | Saturday | Complete Integration | 20
Day26 | 2019-06-17 | Monday | Bugs and Errors | 7
Day27 | 2019-06-19 | Wednesday | Planning | 4
Day28 | 2019-06-20 | Thursday | Information Gathering | 3
Day29 | 2019-06-22 | Saturday | Teacher Intimation | -
Day30 | 2019-07-01 | Monday | Planning and Design | 3
Day31 | 2019-07-03 | Wednesday | HOD Sir Permission | -
Day32 | 2019-07-15 | Monday | Mitali Maam | -
Day33 | 2019-07-16 | Tuesday | Presentation Intro | -
Day34 | 2019-07-17 | Wednesday | Polytechnic Reference | -
Day35 | 2019-07-19 | Friday | Architechture and Bugs | 3
Day36 | 2019-07-22 | Monday | Polytechnic for SPI Bug
Day37 | 2019-07-24 | Wednesday | Bugs and Errors | 3
Day38 | 2019-07-29 | Monday | Bugs and Errors | 3
Day39 | 2019-08-02 | Friday | Database Design Reloaded | 5
Day40 | 2019-08-03 | Saturday | GUI Reloaded | 4
Day41 | 2019-08-05 | Monday | Startup Form | -
Day42 | 2019-08-07 | Wednesday | Logo | 3
Day43 | 2019-08-08 | Thursday | Polytechnic for Startup Fund | -
Day44 | 2019-08-09 | Friday | MicroProcessor Research | 4
Day45 | 2019-08-10 | Saturday | Login Rebirth | 5
Day46 | 2019-08-11 | Sunday | GUI Update | 3
Day47 | 2019-08-12 | Monday | Raspeberry Pi Begins | 5
Day48 | 2019-08-16 | Friday | OTP with Email | 5
Day49 | 2019-08-17 | Saturday | Real MySQL Escape | 2
Day50 | 2019-08-20 | Tuesday | Fingerprint Template Generation | 15
Day51 | 2019-08-22 | Thursday | Startup Detail Gathering (Pavillion) | -
|  |  | Internal Exams | -
Day52 | 2019-09-01 | Sunday | Switch to Github | 6
Day53 | 2019-09-03 | Tuesday | Fingerprint Research, RTC with Rpi | 4
Day54 | 2019-09-04 | Wednesday | Screen with Rpi, Figuring Git | 5
Day55 | 2019-09-05 | Thursday | Unlimited Fingerprint Milestone | 18
Day56 | 2019-09-06 | Friday | Fingerprint Testing | 8
Day57 | 2019-09-08 | Sunday | Netbeans with Git | 3
Day58 | 2019-09-09 | Monday | Organization on Github | 4
Day59 | 2019-09-10 | Tuesday | Database Rebirth | 15
Day60 | 2019-09-12 | Thursday | Rpi Sync Function | 13
Day61 | 2019-09-13 | Friday | SQL just got crazy | 5
|  |  | Practical Exams | -
Day62 | 2019-09-24 | Tuesday | Bugs GUI | 2
Day63 | 2019-09-26 | Thursday | Documentation | 4
Day64 | 2019-09-27 | Friday | Internal Presentation | 10
368

## Sheet2
S.No. | Product Backlog Item | Task | Volunteer | Status | Original Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9
1 | Requirements for Attendance | Research and Buy Components | Vraj | Completed | 20 | 2 | 3 | 2 | 2 | 4 | 3 | 0 | 2 | 4
2 |  | Testing Separate Components | Ebenezer | Completed | 20 | 5 | 8 | 4 | 7 | 9 | 3 | 4 | 2 | 4
3 | Website to Check Attendance | Demo Servlet | Ebenezer | Completed | 10 | 4 | 1 | 3 | 0 | 1 | 0 | 2 | 0 | 1
4 | Want look and feel | Make Box | Ebenezer | Completed | 40 | 15 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0
5 |  | Make changes in Arduino Libraries | Ebenezer | Completed | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0
6 | Standby to Save Power | LightShow for StandBy | Ebenezer | Completed | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
7 | Want to store time | RTC bug Fixing | Vraj | Discontinued | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0
8 | Want Ethernet and SD Card | Zerner Diode | Vraj | Discontinued | 100 | 10 | 11 | 13 | 15 | 14 | 9 | 12 | 6 | 17
9 | Want to increase Storage Space | Dividing FPS Storage Space | Ebenezer | Discontinued | 100 | 11 | 13 | 12 | 10 | 9 | 15 | 0 | 15 | 13
|  |  |  | Actual Hours remaining | 50 | 47 | 53 | 46 | 37 | 37 | 30 | 21 | 25 | 39
|  |  |  | Estimated Remaining Hours | 50 | 46 | 42 | 38 | 34 | 30 | 26 | 22 | 18 | 14
|  |  |  | Estimated Working Hours | 50 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2