## Sheet1
Date | Working Hours |  |  | Total Hours | Worked on which Task |  |  | Total Task Completed
| Ebenezer | Husein | Vraj |  | Ebenezer | Husein | Vraj
2019-09-27 | 9 |  | 8 | 17 | Rpi demo debugging, light show, perf board designing |  | Documentation, Order from ROBU | 4
2019-09-28 | 5 |  | 0 | 5 | perf board adding modules - eth, rtc |  | - | 1
2019-09-29 | 9 |  | 0 | 9 | buzzer function, perf board adding modules - rtc, fps, buzzer |  | - | 3
2019-09-30 | 0 |  | 3 | 3 |  |  | sql queries, manage timetable | 2
2019-10-01 | 8 |  | 0.5 | 8.5 | lcd testing |  | Rpi testing with projecting gui | 0
2019-10-02 | 7 |  | 7 | 14 | lcd testing |  | editTimetable Servlet, Database(MAJOR), ERD | 4
2019-10-03 | 5 |  | 2 | 7 | lcd testing |  | minor changes in servlet | 1
2019-10-04 | 4 |  | 4 | 8 | servlets,finance |  | servlets, validations, finance | 3
2019-10-05 |  |  |  | 0
2019-10-06 |  |  |  | 0
2019-10-07 |  |  |  | 0